## Sample
Task name | Planned Start Date | Planned Finish Date | Assigned | Complete |  | Feb (1) |  |  |  |  | Feb (2) |  |  |  |  | Feb (3) |  |  |  |  | Feb (4) |  |  |  |  | Mar (1) |  |  |  |  | Mar (2) |  |  |  |  | Mar (3) |  |  |  |  | Mar (4)
[6 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1.Analysis |  |  |  |  | FALSE
On site meeting |  |  |  |  | TRUE
Discussions with Stakeolders |  |  |  |  | TRUE
Document Current system |  |  |  |  | TRUE
Analysis complete |  |  |  |  | TRUE
2.Design
Design database
Software Design | [5 empty] | Feb (1) M: Total; Feb (1) T: 5
Interface Design | [5 empty] | Feb (1) M: Completed; Feb (1) T: 4
Create Design Specification | [5 empty] | Feb (1) M: %; Feb (1) T: 0
Design complete
No
3.Development
Develop System Modules
Integrate System Module
Perform Initial Testing
Development Complete
4.Testing
Perform System Testing
Document Issues Found
Correct Issues found
Testing Complete
5.Implementation
On-site Installation
Setup Database
Import Live data

## Testing
Hello | id | age | name | faulty | fees
| 1 | 21 | kamal | foe | 1234 |  |  | SD | CD
|  | 21 | kamal | foc | 2345 |  |  | 2019-01-01 | 2019-01-02
| 3 | 23 | nimal | foe | 4321 |  |  | 2019-01-15 | 2019-04-04
| 4 | 22 | sunimal | archi | 6543 |  |  | 2019-01-22 | 2019-03-05
| 5 | 23 | peter | archi | 7654 | foc | 10
| 6 | 21 | jane | foc | 6000 | foe | 8
| 7 | 21 | kamal | foc | 4000 | archi | 6
| 8 | 23 | jhon | foe | 2000
| 9 | 22 | gerry | foc | 1000 |  |  |  | 2
| 10 | 24 | nadun | foe | 9000 |  |  |  | 58
| 11 | 21 | kamal | foe | 9000 | foc & kamal | 5
| 12 | 21 | nimal | foc | 8000 | [5 empty] | today | 2019-03-28
| 13 | 23 | nimal | foe | 5000 |  |  | Start date | Close date | dates worked | Column1
| 14 | 22 | sunimal | archi | 4000 |  |  | 2019-03-05 |  | 18 | Average
| 15 | 23 | peter | archi | 5000 |  |  | 2019-01-15 |  | 53 | FALSE
| 16 | 21 | jane | foc | 6578 |  |  | 2019-01-22 |  | 48 | FALSE
| 17 | 21 | kamal | foc | 6765
| 18 | 23 | jane | foe | 546
| 19 | 22 | gerry | foe | 465
| 20 | 24 | nadun | archi | 5667
|  |  | kamal | foc
|  |  | kamal | foc
archi
foc

## Mobitel
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37 | Column38 | Column39 | Column40 | Column41 | Column42 | Column43 | Column44 | Column45 | Column46 | Column47 | Column48 | Column49 | Column50 | Column51 | Column52 | Column53 | Column54 | Column55 | Column56 | Column57 | Column58 | Column59 | Column60 | Column61 | Column62 | Column63 | Column64 | Column65 | Column66 | Column67 | Column68 | Column69 | Column70 | Column71 | Column72 | Column73 | Column74 | Column75 | Column76 | Column77 | Column78 | Column79 | Column80 | Column81 | Column82 | Column83 | Column84 | Column85 | Column86 | Column87 | Column88 | Column89 | Column90 | Column91 | Column92 | Column93 | Column94 | Column95 | Column96 | Column97 | Column98 | Column99 | Column100 | Column101 | Column102 | Column103 | Column104 | Column105 | Column106 | Column107 | Column108 | Column109 | Column110 | Column111 | Column112 | Column113 | Column114 | Column115 | Column116 | Column117 | Column118 | Column119 | Column120 | Column121 | Column122 | Column123 | Column124 | Column125 | Column126 | Column127 | Column128 | Column129 | Column130 | Column131 | Column132 | Column133 | Column134 | Column135 | Column136 | Column137 | Column138 | Column139 | Column140 | Column141 | Column142 | Column143 | Column144 | Column145 | Column146 | Column147 | Column148 | Column149 | Column150 | Column151 | Column152 | Column153 | Column154 | Column155 | Column156 | Column157
Column1: Task name; Column2: Start Date; Column3: Finish Date; Column4: Assigned; Column5: Complete; Column6: Feb (1); Column8: 1; Column11: Feb (2); Column13: 2; Column16: Feb (3); Column18: 3; Column21: Feb (4); Column23: 4; Column26: Mar (1); Column28: 5; Column31: Mar (2); Column33: 6; Column36: Mar (3); Column38: 7; Column41: Mar (4); Column43: 8; Column46: Mar (4); Column48: 9; Column51: Mar (4); Column53: 10; Column56: Mar (4); Column58: 11; Column61: Mar (4); Column63: 12; Column66: Mar (4); Column68: 13; Column71: Mar (4); Column73: 14; Column76: Mar (4); Column78: 15; Column81: Mar (4); Column83: 16; Column86: Mar (4); Column88: 17; Column91: Mar (4); Column93: 18; Column96: Mar (4); Column98: 19 |  | Mar (4) |  | 20 |  |  | Mar (4) |  | 21 |  |  | Mar (4) |  | 22 |  |  | Mar (4) |  | 23 |  |  | Mar (4) |  | 24 |  |  | Mar (4) |  | 25 |  |  | Mar (4) |  | 26 |  |  | Mar (4) |  | 27 |  |  | Mar (4) |  | 28 |  |  | Mar (4) |  | 29 |  |  | Mar (4) |  | 30 |  |  | Mar (4)
 | time axis 2019-02-03 to 2019-07-04
1.Analysis
Discussing the process
Discussions with Stakeholders
Document Current system
Analysis complete
2.Design
Design database (ER)
Software Design and refer
Interface Design
Create Design Specification
Design complete
3.Development
Home pages
Relevant tutorials
Help
Back-end
4.Testing
Perform System Testing
Document Issues Found
Correct Issues found
Testing Complete
5.Implementation
On-site Installation
Setup Database
Import Live data

## ITPM
Task name | Start Date | Finish Date | Assigned | Complete |  |  |  | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [7 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13
 | time axis 2019-02-04 to 2019-05-05
Discussing the process & Dividing tasks |  |  | Kirul |  | TRUE | 2019-02-16: meeting
Designing week |  |  | Group |  | TRUE | bar: 2019-02-16 to 2019-02-17
Documentation (project Backlog) |  |  | Group |  | TRUE | bar: 2019-02-15 to 2019-02-16
Analysis complete |  |  | Group |  | TRUE | bar: 2019-02-15 to 2019-02-17
Analysis |  |  |  |  | TRUE | bar: 2019-02-04 to 2019-02-17
Design database (ER) |  |  | Group |  | TRUE | bar: 2019-02-18 to 2019-02-24
Software Design |  |  | Group |  | TRUE
Interface Design |  |  | Group |  | TRUE
Design - Backlog and |  |  |  |  | TRUE | bar: 2019-02-11 to 2019-02-17
Home page |  |  | Group |  | TRUE | bar: 2019-02-25 to 2019-02-26
Books CRUD |  |  | Dep |  | TRUE
User levels(Login/ Register) |  |  | Rashmini |  | TRUE
Book handling |  |  | Rika |  | TRUE
Accounts handling |  |  | Kirul |  | FALSE
Noticification / Membership Update |  |  | Sandeepa |  | FALSE
Developing - sprint 1 |  |  |  |  | FALSE | bar: 2019-02-18 to 2019-03-17
Perform System Testing |  |  | Kirul / Sandeepa |  | FALSE
Document Issues Found |  |  | Kirul / Sandeepa |  | FALSE
Correct Issues found |  |  | Kirul / Sandeepa |  | FALSE
Testing Complete |  |  | Kirul / Sandeepa |  | FALSE
Automated Testing |  |  |  |  | FALSE | bar: 2019-03-18 to 2019-03-24
check smoke testing |  |  | Rashmini |  | FALSE
Implementing |  |  | Kirul / Sandeepa |  | FALSE
Smoke Testing |  |  |  |  | FALSE | bar: 2019-03-25 to 2019-03-31
BooksFunction |  |  | Dep |  | FALSE
User Level Function |  |  | Rashmini |  | FALSE
Books handling fuctions |  |  | Rika |  | FALSE
Calculations |  |  | Kirul |  | FALSE
Notifying via mails/ SMS |  |  | Sandeepa |  | FALSE
Developing - sprint 2 |  |  |  |  | FALSE | bar: 2019-04-01 to 2019-04-14
Testing the whole Project |  |  |  |  | FALSE
Debugging |  |  |  |  | FALSE
Case Study |  |  |  |  | FALSE | bar: 2019-04-15 to 2019-04-21
Finalizing |  |  |  |  | FALSE | bar: 2019-04-22 to 2019-05-05
Total Tasks | 34
Completed Tasks | 38.2353 | %

## Sheet1
testing after uploadiing extrail
github upload testing
| SD | CD
| 2019-01-01 | 2019-01-02
| 2019-01-15 | 2019-04-04
| 2019-01-22 | 2019-03-05
Full Screen

## Minisa7.0
Opportunity Name : Minisa 7.0
Opportunity ID :
42 Day Plan
Week | Day No | Date | Day | Job | Status | Delivered | Remarks
1 | 1 | 2019-01-15 | Tuesday | Project Planning | Confirmed
| 2 | 2019-01-16 | Wednesday | Pick up Gamze | Confirmed
|  |  |  | Pick up Rita | Confirmed
| 3 | 2019-01-17 | Thursday | Team Bonding Session | Confirmed
| 4 | 2019-01-18 | Friday | Visit to Kaluthara Bhodiya | Confirmed
| 5 | 2019-01-19 | Saturday | Visit to Wadduwa Beach | Confirmed
| 6 | 2019-01-20 | Sunday | Colombo Tour | Confirmed
|  |  |  | Pick up Sherry | Confirmed
| 7 | 2019-01-21 | Monday | Incoming Preperation Seminar | Confirmed
2 | 8 | 2019-02-22 | Tuesday | Initial visit to Marcsri Homes | Confirmed
| 9 | 2019-01-23 | Wednesday | Project Session | Confirmed
| 10 | 2019-01-24 | Thursday | Project Session | Confirmed
| 11 | 2019-01-25 | Friday | Visit to Sinharaja Forest | Confirmed
| 12 | 2019-01-26 | Saturday | Vinul's Birthday Party | Confirmed
| 13 | 2019-01-27 | Sunday | Holiday | Confirmed
| 14 | 2019-01-28 | Monday | Project Session | Confirmed
3 | 15 | 2019-01-29 | Tuesday | Project Session | Confirmed
| 16 | 2019-01-30 | Wednesday | Project Session | Confirmed
| 17 | 2019-01-31 | Thursday | Project Session | Confirmed
| 18 | 2019-02-01 | Friday | Project Session | Cancelled |  | Trip to Yala
| 19 | 2019-02-02 | Saturday | Yala National Park Trip | Confirmed
| 20 | 2019-02-03 | Sunday | Yala National Park Trip | Confirmed
| 21 | 2019-02-04 | Monday | Independence Day | Confirmed |  | Visit to Galle
4 | 22 | 2019-02-05 | Tuesday | Chinese Spring Festival | Confirmed
| 23 | 2019-02-06 | Wednesday | Project Session | In Progress
| 24 | 2019-02-07 | Thursday | Project Session | In Progress
| 25 | 2019-02-08 | Friday | Project Session | In Progress
| 26 | 2019-02-09 | Saturday |  | In Progress
| 27 | 2019-02-10 | Sunday |  | In Progress
| 28 | 2019-02-11 | Monday | Project Session | In Progress
5 | 29 | 2019-02-12 | Tuesday | Project Session | In Progress
| 30 | 2019-02-13 | Wednesday | Project Session | In Progress
|  |  |  | Sugar Cubes Date | In Progress
| 31 | 2019-02-14 | Thursday | Winter Global Village | In Progress |  | Rita leaves
|  |  |  | Drop Rita at the Airport | In Progress
| 32 | 2019-02-15 | Friday |  | In Progress
| 33 | 2019-02-16 | Saturday |  | In Progress
| 34 | 2019-02-17 | Sunday |  | In Progress
| 35 | 2019-02-18 | Monday |  | In Progress
6 | 36 | 2019-02-19 | Tuesday |  | In Progress
| 37 | 2019-02-20 | Wednesday | Drop Sherry at the Airport | In Progress |  | Sherry leaves
| 38 | 2019-02-21 | Thursday |  | In Progress
| 39 | 2019-02-22 | Friday |  | In Progress
| 40 | 2019-02-23 | Saturday |  | In Progress
| 41 | 2019-02-24 | Sunday |  | In Progress
| 42 | 2019-02-25 | Monday |  | In Progress